## 5
Name | Ref. number | Project Involvement | PE | Discipline | Assigned Tasks (Summary) | Work Duration | Month Started | Week Started | Target Work Hours | Actual Work Hours | % Accomplishment | Efficiency | Status | Quality Score | QS% | Revision/s | Month Completed | Week Completed | Date Completed
Gabrielle Gameng | 0001A | 284.北昌模型修正 | 王郁茹 | AS | AS Modelling | 20250407-20250418 | April | 2 | 80 | 64 | 1 | 125% | Completed | 84% | 0.84 | 0.2 | April | 3 | 20250415
Gabrielle Gameng | 0002A | 293.白鷺安居 | 邵啟立 | AS | AS Modelling | 20250415-20250421 | April | 3 | 24 | 16 | 1 | 150% | Completed | 90% | 0.9 | 0 | April | 3 | 20250421
Gabrielle Gameng | 0004A | 242.桃園T3指標工程BIM建置服務 | 陳威達 | AS | Family Creation and Placement | 20250428-20250516 | April | 4 | 112 | 108 | 1 | 103.7% | Completed | 92% | 0.92 | 0.2 | May | 3 | 20250516
Gabrielle Gameng | 0005A | 220.桃園長庚醫院 | Chris | MEP | Sheeting and Exporting CAD | 20250514-20250529 | May | 3 | 104 | 90 | 1 | 115.6% | Completed | 98% | 0.98 | 0 | June | 2 | 20250613
Gabrielle Gameng | 0006A | 293.白鷺安居 | 邵啟立 | AS | AS Modelling | 20250523-20250527 | May | 4 | 20 | 21 | 1 | 95.24% | Completed | 100% | 1 | 0 | May | 5 | 20250528
Gabrielle Gameng | 0007A | 286.台北長庚 | Chris | AS | AS Modelling | 20250602-20250605 | June | 1 | 32 | 32 | 1 | 100% | Completed | 100% | 1 | 0 | June | 1 | 20250605
Gabrielle Gameng | 0008A | 242.桃園T3指標工程BIM建置服務 | 陳威達 | AS | Family Creation and Placement | 20250605-20250609 | June | 1 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | June | 2 | 20250609
Gabrielle Gameng | 0009A | 286.台北長庚 | Chris | AS | AS Modelling, Family Modelling | 20250609-20250611 | June | 2 | 32 | 32 | 1 | 100% | Completed | 100% | 1 | 0 | June | 2 | 20250611
Gabrielle Gameng | 0010A | 286.台北長庚 | Chris | AS | AS Modelling (1F-6F) | 20250616-20250618 | June | 3 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | June | 3 | 20250618
Gabrielle Gameng | 0011A | 240. 桃園市龜山 | Tiziana | MEP | MEP Modelling (Gas System) | 20250620-20250627 | June | 4 | 48 | 56 | 1 | 85.71% | Completed | 80% | 0.8 | 0.4 | July | 1 | 20250702
Gabrielle Gameng | 0012A | 220.桃園長庚醫院 | Chris | MEP | MEP File Separation | 20250703-20250704 | July | 1 | 16 | 12 | 1 | 133.3% | Completed | 100% | 1 | 0 | July | 1 | 20250704
Gabrielle Gameng | 0013A | 192.岡山大鵬 | Wayne | AS | AS model modification | 20250707-20250711 | July | 1 | 40 | 40 | 1 | 100% | Completed | 100% | 1 | 0 | July | 2 | 20250711
Gabrielle Gameng | 0014A | 230.前寮龍岡好室 | Willy | RFA | Family Modification | 20250715-20250717 | July | 2 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | July | 3 | 20250717
Gabrielle Gameng | 0015A | 216.美崙安居 | Tiziana | RFA | Family Modification | 20250721-20250725 | July | 4 | 40 | 40 | 1 | 100% | Completed | 100% | 1 | 0 | July | 4 | 20250725
Gabrielle Gameng | 0016A | 286.台北長庚 | Chris | AS | AS Modelling | 20250722-20250728 | July | 4 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | July | 4 | 20250729
Gabrielle Gameng | 0017A | 198.文人安居 | Tiziana | AS | AS Ceiling Modification | 20250729-20250730 | July | 4 | 12 | 24 | 1 | 50% | Completed | 90% | 0.9 | 0.4 | July | 4 | 20250731
Gabrielle Gameng | 0018A | 216.美崙安居 | Tiziana | RFA | Family Modification and Placing | 20250730-20250811 | July | 4 | 40 | 40 | 1 | 100% | Completed | 100% | 1 | 0.2 | August | 2 | 20250811
Gabrielle Gameng | 0019A | 240. 桃園市龜山 | Tiziana | RFA | MEP Modelling (Gas System) | 20250813-20250815 | August | 2 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0.2 | August | 2 | 20250819
Gabrielle Gameng | 0020A | 嘉義長庚 | Chris | AS | AR modelling | 20250819-20250821 | August | 3 | 16 | 16 | 1 | 100% | Completed | 96% | 0.96 | 0 | August | 3 | 20250821
Gabrielle Gameng | 0021A | 244.勝利安居 | Joy | AS | AS modification | 20250821-20250827 | August | 3 | 40 | 42 | 1 | 95.24% | Completed | 96% | 0.96 | 0.4 | August | 4 | 20250827
Gabrielle Gameng | 0022A | 嘉義長庚 | Chris | AS | AR modelling | 20250828-20250902 | August | 4 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | September | 1 | 20250902
Gabrielle Gameng | 0023A | 242.桃園T3指標工程BIM建置服務 | 陳威達 | AS | Family Placement | 20250902-20250904 | September | 1 | 24 | 16 | 0.66667 |  | on-going
Gabrielle Gameng | 0024A | 244.勝利安居 | Joy | AS | AS modification | 20250821-20250827 | September | 1
Belinda | 0001D | 214.和順安居 |  | MEP | MEP modelling | 20250618-20250624 | June | 3 | 16 | 17.25 | 1 | 92.75% | Completed | 100% | 1 | 0 | June | 2 | 20250624
Belinda | 0002D | 267.芝山安居 |  | MEP | MEP modelling | 20250701-20250703 | July | 1 | 16 | 5.33 | 1 | 300.2% | Completed | 100% | 1 | 0 | July | 3 | 20250703
Belinda | 0003D | 233.光環安居 |  | MEP | MEP modelling | 20250701-20250709 | July | 1 | 24 | 84.33 | 1 | 28.46% | Completed | 100% | 1 | 0.2 | July | 3 | 20250713
Belinda | 0004D | 214.和順安居 |  | MEP | MEP modelling | 20250711-20250718 | July | 2 | 24 | 9.33 | 1 | 257.2% | Completed | 100% | 1 | 0.4 | July | 3 | 20250721
Belinda | 0005D | 267.芝山安居 |  | MEP | MEP modelling | 20250722-20250728 | July | 2 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | July | 4 | 20250728
Belinda | 0006D | 290.坤門安居 |  | MEP | MEP modelling | 20250728-20250815 | July | 4 | 80 | 172.33 | 1 | 46.42% | Completed | 100% | 1 | 0.4 | September | 1 | 20250903
Belinda | 0007D | 233.光環安居 |  | MEP | MEP modelling | 20250822-20250828 | August | 3 | 40 | 15.5 | 1 | 258.1% | Completed | 100% | 1 | 0.2 | August | 4 | 20250828
Raymond Navarro | 0001C | 284.北昌模型修正 | 王郁茹 | AS | AS Model Modification | 20250623-20250704 | June | 4 | 80 | 72 | 1 | 111.1% | Completed | 100% | 1 | 0.2 | July | 1 | 20250703
Raymond Navarro | 0002C | 240.樂善安居 | Tiziana | MEP | MEP Modification (EE) | 20250704-20250707 | July | 1 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | July | 2 | 20250708
Raymond Navarro | 0003C | 240.樂善安居 | Tiziana | AS | AS Model Modification | 20250709-20250711 | July | 2 | 16 | 20 | 1 | 80% | Completed | 96% | 0.96 | 0.6 | July | 2 | 20250715
Raymond Navarro | 0005C | 218.萬大線 | Mars | SEM | SEM Model Modification | 20250718-20250722 | July | 3 | 24 | 24 | 1 | 100% | Completed | 100% | 1 | 0 | July | 4 | 20250722
Raymond Navarro | 0006C | 嘉義長庚 | Tiziana | ST | ST Modelling from Start | 20250728-20250811 | July | 4 | 80 | 88 | 1 | 90.91% | Completed | 100% | 1 | 0 | August | 2 | 20250811
Raymond Navarro | 0007C | 291.福清安居 | Tiziana | AS | Excavation Model Creation | 20250814-20250815 | August | 2 | 16 | 14 | 1 | 114.3% | Completed | 100% | 1 | 0 | August | 2 | 20250815
Raymond Navarro | 0008C | 218.萬大線 | Mars | SEN | SEM Model Modification | 20250815-20250822 | August | 2 | 32 | 48 | 1 | 66.67% | Completed | 60% | 0.6 | 0.6 | August | 3 | 20250822
Raymond Navarro | 0009C | 284.北昌模型修正 | 王郁茹 | AS | AS Model Modification | 20250822-20250829 | August | 3 | 40 | 56 | 1 | 71.43% | Completed | 88% | 0.88 | 0.6 | September | 1 | 20250903
Carlo Nilo | 0001E | 284.北昌模型修正 | 王郁茹 | AS | AS Modelling | 20250723-20250730 | July | 3 | 80 | 80 | 1 | 100% | Completed | 90% | 0.9 | 0.2 | August | 2 | 20250801
Carlo Nilo | 0002E | 215. 高雄捷運RKC02標 | Chris | AS | ST Modelling (Substructure RFA) | 20250730-20250808 | July | 4 | 32 | 32 | 1 | 100% | Completed | 96% | 0.96 | 0.4 | August | 1 | 20250805
Carlo Nilo | 0003E | 215. 高雄捷運RKC02標 | Chris | AS | ST Modelling (Substructure RFA) | 20250811-20250815 | August | 2 | 40 | 40 | 1 | 100% | Completed | 100% | 1 | 0.4 | August | 2 | 20250815
Carlo Nilo | 0004E | 244.勝利安居 | Joy | AS | AS modification | 20250821-20250827 | August | 3 | 40 | 48 | 1 | 83.33% | Completed | 92% | 0.92 | 0.4 | August | 4 | 20250828
Carlo Nilo | 0005E | 265.鯤鯓安居 | Wayne | AS | AS modification and RFA placing | 20250828-20250904 | August | 4 | 40 | 32 | 0.8 |  | On-going
Jonica Jomadiao | 0001F | 284.北昌模型修正 | 王郁茹 | AS | AS Modelling | 20250726-20250729 | July | 3 | 24 | 24 | 1 | 100% | Completed | 96% | 0.96 | 0.1 | August | 2 | 20250801
Jonica Jomadiao | 0002F | 244.勝利安居 | Joy | AS | AS modification | 20250821-20250827 | August | 3 | 40 | 40 | 1 | 100% | Completed | 96% | 0.96 | 0.1 | August | 4 | 20250828
Jonica Jomadiao | 0003F | 265.鯤鯓安居 | Wayne | AS | AS modification and RFA placing | 20250828-20250904 | August | 4 | 40 | 32 | 0.8 |  | On-going