## 1
Name | Ref. number | Project Involvement | PE | Discipline | Assigned Tasks (Summary) | Work Duration | Month Started | Week Started | Target Work Hours | Actual Work Hours | % Accomplishment | Efficiency | Status | Quality Score | QS% | Revision/s | Month Completed | Week Completed | Date Completed
Raymond Navarro | 0001C | 284.北昌模型修正 | 王郁茹 | AS | AS Model Modification | 20250623-20250704 | June | 4 | 80 | 72 | 1 | 1.1111 | Completed | 5 | 1 | 0.2 | July | 1 | 20250703
Raymond Navarro | 0002C | 240.樂善安居 | Tiziana | MEP | MEP Modification (EE) | 20250704-20250707 | July | 1 | 24 | 24 | 1 | 1 | Completed | 5 | 1 | 0 | July | 2 | 20250708
Raymond Navarro | 0003C | 240.樂善安居 | Tiziana | AS | AS Model Modification | 20250709-20250711 | July | 2 | 16 | 20 | 1 | 0.8 | Completed | 4.8 | 0.96 | 0.6 | July | 2 | 20250715
Raymond Navarro | 0005C | 218.萬大線 | Mars | SEM | SEM Model Modification | 20250718-20250722 | July | 3 | 24 | 24 | 1 | 1 | Completed | 5 | 1 | 0 | July | 4 | 20250722
Raymond Navarro | 0006C | 嘉義長庚 | Tiziana | ST | ST Modelling from Start | 20250728-20250811 | July | 4 | 80 | 88 | 1 | 0.90909 | Completed | 5 | 1 | 0 | August | 2 | 20250811
Raymond Navarro | 0007C | 291.福清安居 | Tiziana | AS | Excavation Model Creation | 20250814-20250815 | August | 2 | 16 | 14 | 1 | 1.1429 | Completed | 5 | 1 | 0 | August | 2 | 20250815
Raymond Navarro | 0008C | 218.萬大線 | Mars | SEN | SEM Model Modification | 20250815-20250822 | August | 2 | 32 | 48 | 1 | 0.66667 | Completed | 3 | 0.6 | 0.6 | August | 3 | 20250822
Raymond Navarro | 0009C | 284.北昌模型修正 | 王郁茹 | AS | AS Model Modification | 20250822-20250829 | August | 3 | 40 | 56 | 1 | 0.71429 | Completed | 4.4 | 0.88 | 0.6 | September | 1 | 20250903